FINAL EXECUTION PLAN

May 20 → June 10 · 3 People Full-Time · Win on Correctness

IICPC Summer Hackathon 2026 — Distributed Benchmarking Platform

Verified facts: start 20 May · submit 10 June · ~18 effective build days · nothing built yet

Consolidates 5 architecture docs + the win strategy + the two good external ideas.

# Table of Contents

# 1. The Situation, Stated Without Optimism

| Fact | Value (verified, not assumed) |
| --- | --- |
| Start date | 20 May 2026 (today). Nothing built. The 11 days since 9 May are gone. |
| Submission | 10 June 2026. |
| Calendar days | 21. |
| Effective build days | ~18 (last 2 frozen for rehearsal + submission buffer; integration always overruns). |
| Team | 3 people, full-time, AI-accelerated. |
| Field | Top-tier; also AI-accelerated (IICPC encourages heavy AI use). |

The one belief to discard before starting “Heavy AI use means time is not a problem” is false in the way that matters. AI accelerates thinking and scaffolding; it does not accelerate integration, and integration is where this is won or lost. Every competing team is equally AI-accelerated, so AI speed is the baseline, not the edge. The edge is being provably correct where a fast-moving field is confidently wrong. AI abundance makes that edge more valuable, because more teams will ship fast, unverified p99s.

# 2. The Winning Thesis

Against a top-tier, AI-accelerated field, breadth loses — everyone builds broad and fast. You win by being unambiguously correct about the one thing most teams get wrong, and proving it live. That thing is Coordinated Omission: closed-loop load generators silently drop their worst latency samples, making p99 wrong by up to two orders of magnitude. Strong teams ship this bug too. A side-by-side demo of the same run — naive p99 vs CO-corrected p99, ~50× apart — proves your platform measures reality and implies the rest of the field’s numbers are fiction. Sophisticated judges grasp that instantly.

The build, in one sentence One thin pipeline that is provably correct, with the CO proof as the centerpiece; the Ephemeral Batching Queue folded in for honest scale; SIMD documented but not built; everything else deferred and defended as engineering judgment.

# 3. Scope: Build / Fold-In / Defer

Full-time × 3 × 18 days × AI is a comfortable margin for the scope below — the risk is scope creep eating the buffer, never the hours. The extra days over a 15-day plan buy safety margin, not extra features.

| BUILD (the spine) | FOLD IN (the 2 good external ideas) | DEFER (documented & defended) |
| --- | --- | --- |
| Open-loop CO-corrected C++ bot | Ephemeral Batching Queue: score 20k in rolling batches of 500 (RabbitMQ/SQS) | AF_XDP kernel bypass |
| Thin end-to-end pipeline | Leaderboard virtual scrolling + WS rank-deltas (no 20k-row DOM crash) | Firecracker/unikernel (Docker/K8s isolation instead) |
| Reference engine + byte-exact diff | Scale-ready framing in the blueprint (writing, not build) | PTP hardware timestamping |
| HDR telemetry → VictoriaMetrics → board | — | SIMD ingester (documented, evidence-gated, not scheduled) |
| One protocol (binary FIX or WS) | — | All three protocols; Aeron (use TCP/UDP+SBE) |

Why SIMD is documented but NOT scheduled — correcting the external plan The external plan scheduled AVX-512 SIMD as a mandatory “flex” on fixed days. This is an error. SBE is fixed-offset — single-message decode is struct overlay, effectively free; SIMD’s only real payoff is batch validation across many messages, and the genuinely branchy win is ASCII FIX, not SBE. Worse, AVX-512 downclocks and is absent on many CPUs; mandating it without a tested fallback risks wrong throughput counts — a correctness failure on a platform whose entire pitch is correctness. SIMD stays evidence-gated: built only if profiling proves the ingester is the bottleneck, which a cold-start team will almost certainly not reach. It goes in the Deferral Roadmap as mature judgment.

# 4. The 21-Day Schedule (3 Roles, Full-Time)

| Role | Owns |
| --- | --- |
| A — Low-Latency C++ | Bot fleet, HdrHistogram CO correction, reference engine + diff |
| B — Infrastructure | Docker sandboxing, Ephemeral Batching Queue, K8s, IaC |
| C — Frontend/Data | VictoriaMetrics, WS server, virtual-scroll leaderboard |

## Week 1 · May 20–26 · Foundation + Attack the Centerpiece Risk First

| Day | A (C++) | B (Infra) | C (Frontend) |
| --- | --- | --- | --- |
| 20 (D1) | ALL: freeze Interface Contract (SBE schema, journal, HDR rule, scoring). No code first. | ← joint | ← joint, then mock data |
| 21 (D2) | Bot skeleton → null-responder | Docker build+deploy trivial echo engine | Leaderboard shell on mocked gauges |
| 22–23 | CENTERPIECE RISK: HdrHistogram + recordValueWithExpectedInterval vs a stalled responder. Prove CO works. | Batching queue spike: enqueue/dequeue 500 dummy jobs | WS server + virtual-scroll list (10k mock rows) |
| 24–26 | Bot → real engine over TCP/UDP+SBE | Queue drives batch of 500 real containers | Board reads real merged HDR |

The Week-1 gate If CO correction is not demonstrably working by end of Day 4 (23 May), stop adding scope and fix it — it is the entire pitch. It is scheduled first, not last, precisely so a slip is discovered with 16 days of runway, not 2.

## Week 2 · May 27–Jun 2 · Pipeline End-to-End + Hard Freeze

| Day | A (C++) | B (Infra) | C (Frontend) |
| --- | --- | --- | --- |
| 27–28 | Reference engine: price-time book, limit/market/cancel, single-writer, deterministic | Batch lifecycle: spawn→score→reap, quotas | Per-protocol board + percentile ladder |
| 29–30 | Byte-exact diff: reference vs contestant from same journal | IaC: Terraform + K8s manifests draft | PTP/clock-quality badge + run identity UI |
| 31 (D12) | INTEGRATION FREEZE — full pipeline upload→deploy→batch→load→score→board, one protocol, all real | ← all hands on integration | ← all hands on integration |
| Jun 1–2 | Soak: 100s synthetic contestants; integrity gate (noisy-bot exclusion) live | Queue scaled toward 20k-volume simulation | Board stable at 10k+ rows under delta load |

## Week 3 · Jun 3–9 · The Demo, Hardening, Rehearsal

| Day | All three — demo & hardening |
| --- | --- |
| Jun 3–4 | Build the CENTERPIECE DEMO: one screen, same run, naive p99 vs CO-corrected p99, gap explained live. |
| Jun 5 | Correctness encore: submit a deliberately-buggy engine (cancel-after-fill race); diff catches it on stage. |
| Jun 6 | Blueprint deliverable = the 5 architecture docs distilled; Deferral Roadmap written as maturity, not apology. |
| Jun 7 | IaC finalized + repeatably demoable. SIMD only if profiling on Jun 1–2 actually demanded it (it likely did not). |
| Jun 8 | CODE FREEZE. Record backup demo video. No new code after this. |
| Jun 9 | Full timed pitch rehearsal ×3. Practice the deferral defense aloud. |

## Submission · Jun 10

Final rehearsal in the morning, submit by early afternoon — never at the deadline. The whole schedule protects this day as buffer, not as work.

# 5. Honest Risk Register

| Risk | Likelihood | Mitigation |
| --- | --- | --- |
| CO proof slips past Day 4 | Medium | Scheduled first; if it slips, descope everything else hard, do not move it |
| Integration hell at freeze | High | Freeze is Day 12 of 21 — 9 days of buffer after it, by design |
| Reference engine non-determinism | Medium | 3 order types only; single-writer; if shaky, demo a narrower correctness case honestly |
| Batching queue instability at scale | Medium | Spiked Week 1, scaled Week 2; demo at proven scale, claim the rest as designed-for |
| Live demo failure | Medium | Backup video recorded Jun 8; never demo live-only |
| Scope creep (the real one) | High | Full-time × AI tempts “just one more feature.” The Deferral Roadmap is the contract; adding back a deferred item requires removing another |
| A competitor also corrects for CO | Low | Then win on pipeline + correctness diff + presentation; that fallback is already built in |

# 6. The Pitch (How the Room Is Won)

- Show it working. 60s: upload → batch deploy → leaderboard moves. It is real.

- The turn. “Every latency number today, including ours a second ago, is probably a lie.” Same run: naive vs CO-corrected p99, ~50× apart.

- The proof. Coordinated Omission in 30s. wrk2, Cassandra-stress, YCSB all had to be fixed for exactly this. Known production rigor, not theory.

- The encore. Buggy engine submitted; byte-exact diff catches the race live. Speed is meaningless if the engine is wrong — and you can prove which is which.

- Close on judgment. One slide: built / folded-in / deferred, and why. “We could have built six subsystems badly. We built one correctly, proved it, and designed it to scale to 20k.”

# 7. Where AI Helps and Where It Cannot

- AI strong: design, the bot/reference-engine skeletons, scaffolding, debugging reasoning, IaC and document generation, pitch structure. Use it heavily here — this is real leverage and the schedule assumes it.

- AI cannot: make the timing actually correct on your hardware, run your integration, or be a continuous partner — each session starts cold. A skeleton that compiles but is subtly wrong about timing is worth less than none because it looks done. The verification is human, full-time, and yours.

The immediate next artifact The Day 2–4 centerpiece: a runnable open-loop bot with HdrHistogram CO correction firing against a null-responder, including the deliberately-stalled-responder test that produces the naive-vs-corrected gap. That single file de-risks the entire plan. Build it first, the moment the Interface Contract is frozen on Day 1.

End — Final Execution Plan. Companion to the 5 architecture documents (the Blueprint deliverable).